## Sprint 2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 03. Property Search | 03.01 | Search by Buy/Rent | Design UI for Buy/Rent toggle | N | 2025-03-27 | 2025-03-27 | 100% | Bhargav Patel
2 | 03. Property Search | 03.01 | Search by Buy/Rent | Implement dropdown for Buy/Rent | N | 2025-03-28 | 2025-03-28 | 100% | Bhumi Ashokbhai Tadhani
3 | 03. Property Search | 03.01 | Search by Buy/Rent | Integrate filter with search logic | Y | 2025-03-28 | 2025-03-29 | 100% | Harsh Deepakkumar Modi
4 | 03. Property Search | 03.01 | Search by Buy/Rent | Test search filter for Buy/Rent | N | 2025-03-28 | 2025-03-29 | 100% | Sai Nadh Battalapalli
5 | 03. Property Search | 03.02 | Search by Location | Design UI for location input | N | 2025-04-01 | 2025-04-02 | 100% | Harsh Deepakkumar Modi
6 | 03. Property Search | 03.02 | Search by Location | Implement search logic for location | N | 2025-04-03 | 2025-04-03 | 100% | Bhargav Patel
7 | 03. Property Search | 03.02 | Search by Location | Validate location input | N | 2025-04-03 | 2025-04-04 | 100% | Nitant Pareshbhai Bhagat
8 | 03. Property Search | 03.02 | Search by Location | Test location search functionality | Y | 2025-04-03 | 2025-04-04 | 100% | Naga Bavana Kolasani
9 | 03. Property Search | 03.03 | Search by Advanced Filters | Add price range fields to UI | N | 2025-04-04 | 2025-04-04 | 100% | Jenisha Bhaveshbhai Gajera
10 | 03. Property Search | 03.03 | Search by Advanced Filters | Add bedroom filter to UI | N | 2025-04-05 | 2025-04-05 | 100% | Sai Nadh Battalapalli
11 | 03. Property Search | 03.03 | Search by Advanced Filters | Implement backend filter logic | N | 2025-04-05 | 2025-04-06 | 100% | Manish Thotakura
12 | 03. Property Search | 03.03 | Search by Advanced Filters | Perform validation on advanced filters | N | 2025-04-05 | 2025-04-06 | 100% | Bhumi Ashokbhai Tadhani
13 | 03. Property Search | 03.03 | Search by Advanced Filters | Test all advanced search filters | Y | 2025-04-05 | 2025-04-06 | 100% | Harsh Deepakkumar Modi
14 | 03. Property Search | 03.04 | Save Favorite Properties | Design UI for favorite icon | N | 2025-04-06 | 2025-04-06 | 100% | Jenisha Bhaveshbhai Gajera
15 | 03. Property Search | 03.04 | Save Favorite Properties | Implement save-to-favorite functionality | N | 2025-04-07 | 2025-04-07 | 100% | Manish Thotakura
16 | 03. Property Search | 03.04 | Save Favorite Properties | Create backend endpoint for saving favorites | N | 2025-04-07 | 2025-04-08 | 100% | Naga Bavana Kolasani
17 | 03. Property Search | 03.04 | Save Favorite Properties | Test saving/removing favorite properties | Y | 2025-04-07 | 2025-04-08 | 100% | Bhargav Patel
18 | 03. Property Search | 03.05 | View Property Information | Design property detail page | N | 2025-04-08 | 2025-04-08 | 100% | Vrajdeep Dilipbhai Lunagariya
19 | 03. Property Search | 03.05 | View Property Information | Integrate property data in UI | Y | 2025-04-09 | 2025-04-09 | 100% | Nitant Pareshbhai Bhagat
20 | 03. Property Search | 03.05 | View Property Information | Implement backend to retrieve property info | N | 2025-04-09 | 2025-04-10 | 100% | Naga Bavana Kolasani
21 | 03. Property Search | 03.05 | View Property Information | Test property detail rendering | N | 2025-04-09 | 2025-04-10 | 100% | Harsh Deepakkumar Modi
22 | 04. Communication & Interaction | 04.01 | Direct Messaging | Design chat UI | N | 2025-04-10 | 2025-04-10 | 100% | Bhargav Patel
23 | 04. Communication & Interaction | 04.01 | Direct Messaging | Implement messaging backend | N | 2025-04-11 | 2025-04-11 | 100% | Bhumi Ashokbhai Tadhani
24 | 04. Communication & Interaction | 04.01 | Direct Messaging | Connect frontend to backend | N | 2025-04-11 | 2025-04-12 | 100% | Vrajdeep Dilipbhai Lunagariya
25 | 04. Communication & Interaction | 04.01 | Direct Messaging | Test sending and receiving messages | Y | 2025-04-11 | 2025-04-12 | 100% | Naga Bavana Kolasani
26 | 07. Sales & Partnerships | 07.01 | Provide a registration portal for agents and agencies | Design agent registration form | N | 2025-04-12 | 2025-04-13 | 100% | Bhargav Patel
27 | 07. Sales & Partnerships | 07.01 | Provide a registration portal for agents and agencies | Implement registration form fields | Y | 2025-04-12 | 2025-04-13 | 100% | Jenisha Bhaveshbhai Gajera
28 | 07. Sales & Partnerships | 07.01 | Provide a registration portal for agents and agencies | Apply field validation | N | 2025-04-13 | 2025-04-14 | 100% | Sai Nadh Battalapalli
29 | 07. Sales & Partnerships | 07.01 | Provide a registration portal for agents and agencies | Test registration flow | N | 2025-04-13 | 2025-04-14 | 100% | Sai Nadh Battalapalli
30 | 08. Marketing | 08.01 | Optimize property listings for search engines | Add SEO meta tags to property pages | N | 2025-04-14 | 2025-04-15 | 100% | Nitant Pareshbhai Bhagat
31 | 08. Marketing | 08.01 | Optimize property listings for search engines | Generate dynamic meta data | N | 2025-04-14 | 2025-04-15 | 100% | Abhishek Sunil Tamboli
32 | 08. Marketing | 08.01 | Optimize property listings for search engines | Submit sitemap to search engine | N | 2025-04-15 | 2025-04-16 | 100% | Jenisha Bhaveshbhai Gajera
33 | 08. Marketing | 08.01 | Optimize property listings for search engines | Verify SEO implementation | N | 2025-04-15 | 2025-04-16 | 100% | Bhargav Patel

## Sprint 3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 04. Communication & Interaction | 04.02 | Schedule Property Visits | Design visit scheduling interface | N | 2025-04-16 | 2025-04-16 | 100% | Naga Bavana Kolasani
2 | 04. Communication & Interaction | 04.02 | Schedule Property Visits | Implement calendar integration | Y | 2025-04-16 | 2025-04-16 | 100% | Manish Thotakura
3 | 04. Communication & Interaction | 04.02 | Schedule Property Visits | Create backend for scheduling logic | N | 2025-04-16 | 2025-04-17 | 100% | Bhumi Ashokbhai Tadhani
4 | 04. Communication & Interaction | 04.02 | Schedule Property Visits | Test property visit booking flow | N | 2025-04-17 | 2025-04-17 | 100% | Abhishek Sunil Tamboli
5 | 04. Communication & Interaction | 04.02 | Schedule Property Visits | Produce Test Design Specification | N | 2025-04-17 | 2025-04-18 | 100% | Manish Thotakura
6 | 04. Communication & Interaction | 04.02 | Schedule Property Visits | Produce Test Case Specification | N | 2025-04-18 | 2025-04-18 | 100% | Naga Bavana Kolasani
7 | 04. Communication & Interaction | 04.03 | Property Inquiries | Design inquiry form UI | N | 2025-04-18 | 2025-04-18 | 100% | Sai Nadh Battalapalli
8 | 04. Communication & Interaction | 04.03 | Property Inquiries | Implement inquiry form backend | N | 2025-04-18 | 2025-04-19 | 100% | Jenisha Bhaveshbhai Gajera
9 | 04. Communication & Interaction | 04.03 | Property Inquiries | Enable agent notification for inquiries | N | 2025-04-19 | 2025-04-19 | 100% | Bhumi Ashokbhai Tadhani
10 | 04. Communication & Interaction | 04.03 | Property Inquiries | Test inquiry submission and responses | Y | 2025-04-19 | 2025-04-19 | 100% | Vrajdeep Dilipbhai Lunagariya
11 | 04. Communication & Interaction | 04.03 | Property Inquiries | Produce Test Design Specification | N | 2025-04-20 | 2025-04-20 | 100% | Naga Bavana Kolasani
12 | 04. Communication & Interaction | 04.03 | Property Inquiries | Produce Test Case Specification | N | 2025-04-20 | 2025-04-20 | 100% | Manish Thotakura
13 | 04. Communication & Interaction | 04.04 | Reviews and ratings for properties and sellers | Design review submission form | N | 2025-04-20 | 2025-04-21 | 100% | Naga Bavana Kolasani
14 | 04. Communication & Interaction | 04.04 | Reviews and ratings for properties and sellers | Implement rating system logic | N | 2025-04-21 | 2025-04-21 | 100% | Nitant Pareshbhai Bhagat
15 | 04. Communication & Interaction | 04.04 | Reviews and ratings for properties and sellers | Integrate with property and seller profiles | N | 2025-04-21 | 2025-04-22 | 100% | Harsh Deepakkumar Modi
16 | 04. Communication & Interaction | 04.04 | Reviews and ratings for properties and sellers | Test posting and displaying reviews | Y | 2025-04-22 | 2025-04-23 | 100% | Naga Bavana Kolasani
17 | 04. Communication & Interaction | 04.04 | Reviews and ratings for properties and sellers | Produce Test Design Specification | N | 2025-04-23 | 2025-04-23 | 100% | Sai Nadh Battalapalli
18 | 04. Communication & Interaction | 04.04 | Reviews and ratings for properties and sellers | Produce Test Case Specification | N | 2025-04-23 | 2025-04-23 | 100% | Manish Thotakura
19 | 05. Transactions & Payments | 05.03 | Invoice generation | Design invoice template | Y | 2025-04-23 | 2025-04-24 | 100% | Sai Nadh Battalapalli
20 | 05. Transactions & Payments | 05.03 | Invoice generation | Create backend logic for invoice creation | N | 2025-04-24 | 2025-04-24 | 100% | Vrajdeep Dilipbhai Lunagariya
21 | 05. Transactions & Payments | 05.03 | Invoice generation | Integrate invoice with booking flow | N | 2025-04-24 | 2025-04-24 | 100% | Bhargav Patel
22 | 05. Transactions & Payments | 05.03 | Invoice generation | Test invoice PDF generation | N | 2025-04-24 | 2025-04-25 | 100% | Vrajdeep Dilipbhai Lunagariya
23 | 05. Transactions & Payments | 05.03 | Invoice generation | Produce Test Design Specification | N | 2025-04-25 | 2025-04-25 | 100% | Naga Bavana Kolasani
24 | 05. Transactions & Payments | 05.03 | Invoice generation | Produce Test Case Specification | N | 2025-04-25 | 2025-04-26 | 100% | Sai Nadh Battalapalli
25 | 06. Product Development | 06.01 | Manage Errors and Technical issues | Setup error tracking system | N | 2025-04-26 | 2025-04-26 | 100% | Abhishek Sunil Tamboli
26 | 06. Product Development | 06.01 | Manage Errors and Technical issues | Create error logging endpoint | N | 2025-04-26 | 2025-04-26 | 100% | Harsh Deepakkumar Modi
27 | 06. Product Development | 06.01 | Manage Errors and Technical issues | Display user-friendly error messages | Y | 2025-04-26 | 2025-04-27 | 100% | Bhumi Ashokbhai Tadhani
28 | 06. Product Development | 06.01 | Manage Errors and Technical issues | Test critical workflows with error scenarios | N | 2025-04-27 | 2025-04-27 | 100% | Manish Thotakura
29 | 06. Product Development | 06.01 | Manage Errors and Technical issues | Produce Test Design Specification | N | 2025-04-27 | 2025-04-28 | 100% | Nitant Pareshbhai Bhagat
30 | 06. Product Development | 06.01 | Manage Errors and Technical issues | Produce Test Case Specification | N | 2025-04-28 | 2025-04-28 | 100% | Harsh Deepakkumar Modi
31 | 06. Product Development | 06.02 | Integrate third-party APIs | Evaluate and finalize APIs | N | 2025-04-28 | 2025-04-28 | 100% | Sai Nadh Battalapalli
32 | 06. Product Development | 06.02 | Integrate third-party APIs | Create middleware for API communication | Y | 2025-04-29 | 2025-04-29 | 100% | Jenisha Bhaveshbhai Gajera
33 | 06. Product Development | 06.02 | Integrate third-party APIs | Test integration with sandbox credentials | N | 2025-04-29 | 2025-04-29 | 100% | Sai Nadh Battalapalli
34 | 06. Product Development | 06.02 | Integrate third-party APIs | Validate third-party API error handling | N | 2025-04-29 | 2025-04-30 | 100% | Abhishek Sunil Tamboli
35 | 06. Product Development | 06.02 | Integrate third-party APIs | Produce Test Design Specification | N | 2025-04-30 | 2025-04-30 | 100% | Sai Nadh Battalapalli
36 | 06. Product Development | 06.02 | Integrate third-party APIs | Produce Test Case Specification | N | 2025-04-30 | 2025-05-01 | 100% | Harsh Deepakkumar Modi
37 | 08. Marketing | 08.02 | Add promotional banners for featured properties | Design banner layout | N | 2025-05-01 | 2025-05-01 | 100% | Nitant Pareshbhai Bhagat
38 | 08. Marketing | 08.02 | Add promotional banners for featured properties | Enable admin to configure banner slots | N | 2025-05-01 | 2025-05-01 | 100% | Jenisha Bhaveshbhai Gajera
39 | 08. Marketing | 08.02 | Add promotional banners for featured properties | Integrate banners with homepage UI | Y | 2025-05-01 | 2025-05-02 | 100% | Harsh Deepakkumar Modi
40 | 08. Marketing | 08.02 | Add promotional banners for featured properties | Test banner visibility and rotation | N | 2025-05-02 | 2025-05-02 | 100% | Bhumi Ashokbhai Tadhani
41 | 08. Marketing | 08.02 | Add promotional banners for featured properties | Produce Test Design Specification | N | 2025-05-02 | 2025-05-03 | 100% | Nitant Pareshbhai Bhagat
42 | 08. Marketing | 08.02 | Add promotional banners for featured properties | Produce Test Case Specification | N | 2025-05-03 | 2025-05-03 | 100% | Jenisha Bhaveshbhai Gajera
43 | 08. Marketing | 08.03 | Enable social media sharing for property listings | Add share buttons on property detail pages | Y | 2025-05-03 | 2025-05-04 | 100% | Nitant Pareshbhai Bhagat
44 | 08. Marketing | 08.03 | Enable social media sharing for property listings | Integrate sharing logic with Facebook, Twitter, etc. | N | 2025-05-04 | 2025-05-04 | 100% | Abhishek Sunil Tamboli
45 | 08. Marketing | 08.03 | Enable social media sharing for property listings | Ensure metadata is SEO-friendly for previews | N | 2025-05-04 | 2025-05-05 | 100% | Nitant Pareshbhai Bhagat
46 | 08. Marketing | 08.03 | Enable social media sharing for property listings | Test sharing functionality end-to-end | N | 2025-05-05 | 2025-05-06 | 100% | Sai Nadh Battalapalli
47 | 08. Marketing | 08.03 | Enable social media sharing for property listings | Produce Test Design Specification | N | 2025-05-06 | 2025-05-07 | 100% | Vrajdeep Dilipbhai Lunagariya
48 | 08. Marketing | 08.03 | Enable social media sharing for property listings | Produce Test Case Specification | N | 2025-05-07 | 2025-05-07 | 100% | Jenisha Bhaveshbhai Gajera