## Road Map
HouseHunt
|  |  | SPRINT 1 | SPRINT 2 | SPRINT 3
Application Modules | Feature Backlog | Story Points | SPRINT1 - 03/26/2025 | SPRINT2 - 04/16/2025 | SPRINT3 - 05/07/2025
01. User Management | 01.01 Create Account | 2 | X
| 01.02 Modify Account | 3 | X
| 01.03 Account Summary | 3 | X
| 01.04 Login functionality | 2 | X
| 01.05 Logout functionality | 1 | X
02. Property Listings | 02.01 Create New Property Listing | 4 | X
| 02.02 Delete Existing Listings | 2 | X
| 02.03 Edit Existing Listings | 3 | X
| 02.04 Upload Images and Videos | 5 | X
| 02.05 Set Property Location | 3 | X
03. Property Search | 03.01 Search by Buy/Rent | 3 |  | X
| 03.02 Search by Location | 3 |  | X
| 03.03 Search by Advanced Filters | 5 |  | X
| 03.04 Save Favorite Properties | 2 |  | X
| 03.05 View Property Information | 3 |  | X
04. Communication & Interaction | 04.01 Direct Messaging | 5 |  | X
| 04.02 Schedule Property Visits | 4 |  |  | X
| 04.03 Property Inquiries | 3 |  |  | X
| 04.04 Reviews and ratings for properties and sellers | 4 |  |  | X
05. Transactions & Payments | 05.01 Secure Payment Processing | 6
| 05.02 Secure Payment Gateway Integration | 5
| 05.03 Invoice generation | 3 |  |  | X
| 05.04 Refunds, chargebacks, and dispute management | 6
06. Product Development | 06.01 Manage Errors and Technical issues | 6 |  |  | X
| 06.02 Integrate third-party APIs | 5 |  |  | X
| 06.03 Performance monitoring and scalability improvements | 7
| 06.04 System updates and maintenance scheduling | 3
07. Sales & Partnerships | 07.01 Provide a registration portal for agents and agencies | 4 |  | X
| 07.02 Onboarding agencies and partners | 4
| 07.03 managing real estate agencies and partners | 5
| 07.04 Display partner performance metrics on the dashboard | 4
08. Marketing | 08.01 Optimize property listings for search engines | 5 |  | X
| 08.02 Add promotional banners for featured properties | 3 |  |  | X
| 08.03 Enable social media sharing for property listings | 3 |  |  | X
| 08.04 Customer engagement tracking and retention strategies | 6
09. Compliance & Legal | 09.01 Require users to accept terms & conditions during sign-up | 2
| 09.02 Add a reporting feature for fraud and policy violations | 4
| 09.03 Managing legal disputes and policy violations | 6
10. Customer Support | 10.01 AI-driven chatbot and automated FAQs | 8
| 10.02 4/7 live chat and ticketing system for user support | 5
| 10.03 User feedback collection and issue resolution tracking | 4
|  | VELOCITY: | 28 | 30 | 31

## Jira Road Map
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## Jira Road Map (Sprint 2)
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board

## Jira Road Map (Sprint 3)
Timeline/Roadmap View: Months
Timeline/Roadmap View: Weeks
Kanban Board (Updated 05/04/2025)